## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

April, 2018 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(5008)/(CE502) [Old/Rev]

# Time Duration: 3 Hrs.                                               Max. Marks: 75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | State qualities of ideal leader |  |
| b) | What is the necessity & importance of planning in construction industry? |  |
| c) | List down role of supervisors on construction site. |  |
| d) | State salient features of co-operative societies. |  |
| e) | Define leaderships & how authoritarian leadership is different from democratic leadership. |  |
| f) | List safety measures adopted at work site for excavation. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Briefly explain work involved in Pre-tender & Post-tender stage. |  |
| b) | How sole proprietorship & partnership contracting firms are managed? State their drawbacks & benefits. |  |
| c) | Write note on “Controlling & Decision making” in construction industry. |  |
| Q.No.3. | Answer the following Questions: |  |
| a) | Construct network diagram & calculate duration of project for activities & their duration stated in table below. Also calculate total float, EST, LST. Mark critical path. | (8) |
| Activity; 1-2; 1-3; 1-4; 2-5; 3-5; 4-7; 3-6; 5-6; 7-8; 4-8; 6-8. Duration (in month); 08; 07; 13; 09; 00; 03; 03; 17; 13; 00; 22. |
| b) | Define float & its uses. | (4) |
| Q.No.4. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain inspection & supervision technique for sanitary & water supply services. |  |
| b) | What are common causes of accidents in construction industry? How can these accidents be prevented? |  |
| c) | What is the importance of quality control for construction? How is it ensured? |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain any one methods of scheduling in construction industry. |  |
| b) | Explain two important types of communication with merits & demerits. |  |
| c) | Write note on “Importance of safety” on construction site. |  |
| Q.No.6. | Write short notes on any three: | 3 x 4 = 12 |
| a) | Workmen Compensation Act |  |
| b) | Equipment management |  |
| c) | Significance of introducing ISO 9000 series |  |
| d) | Site layout |  |
| e) | Principles of management |  |

***********